## Summary
Intellia360 — Functional Gap Analysis
Generated 2026-08-30 ¦ Updated 2026-09-01 (Admin module remediation) ¦ Branch: feature/authentication ¦ Scope: Admin, Teacher, Student, Editor, Auth modules
Total Functional Gaps Identified |  | 33
Fixed (Admin remediation, 2026-09-01) |  | 14
Still Open |  | 19
Severity | Count | % of Total
Critical | 14 | 42.4%
High | 7 | 21.2%
Medium | 7 | 21.2%
Low | 5 | 15.2%
By Status
Status | Count
Fixed | 14
Open | 19
By Module
Module | Gap Count
Admin | 14
Teacher | 7
Student | 10
Editor | 2
Authentication | 0
By Type
Gap Type | Count
Empty Scaffold (Missing Feature) | 11
Mock/Hardcoded Data | 6
Dead Action (No-op) | 3
RBAC Gap | 2
Missing Backend | 2
Incomplete Flow | 2
Broken Link (Integration Gap) | 2
Security Weakness | 1
UI State Gap | 1
Dead Feature (Unused Backend) | 1
Data Integrity/Fabricated Metrics | 1
Broken Link | 1

## Functional Gaps
ID | Module | Feature | Gap | Type | Severity | Status | File/Path | Evidence | Expected Behavior | Current Behavior | Recommended Fix | Complexity | Resolution
GAP-001 | Admin | Route Access Control | Admin pages have no client-side/page-level role guard. | RBAC Gap | Medium | Fixed | src/app/admin/** (no middleware.ts, no admin layout guard) | No src/middleware.ts in repo; admin pages are plain client components with no session/role redirect. Underlying /api/admin/* routes ARE protected server-side. | Non-admin users are redirected away from /admin/* before the page shell renders. | Any signed-in (or unauthenticated) user can load the /admin/* React shell; only the data-fetching API calls are blocked, so pages render as an empty scaffold rather than truly gated. | Add a server-side session/role check in a shared admin layout (or middleware.ts) that redirects non-admin users. | Medium | Fixed 2026-09-01 — added src/app/admin/layout.tsx, a server component that calls getSession() and redirects non-ADMIN users to /login before any admin page renders.
GAP-002 | Admin | Analytics Dashboard | All analytics metrics are hardcoded to 0; nothing is fetched. | Mock/Hardcoded Data | High | Fixed | src/app/admin/analytics/page.tsx:14-30 | avgSessionTime: 0, ... // Replace with API/backend data later | Analytics page shows real platform metrics computed from DB data. | Every metric is a static zero; no fetch call exists in the file. | Build an /api/admin/analytics endpoint aggregating real usage data and wire the page to it. | High | Fixed 2026-09-01 — Quiz Accuracy now computed live from QuizAttempt records via /api/admin/stats; avgSessionTime and activeAIConversations remain 0 (no session/AI-usage tracking model exists yet) rather than being fabricated.
GAP-003 | Admin | Content Library | 'Upload Resource' only pushes to local React state; nothing persists, and no Content model exists. | Missing Backend | High | Fixed | src/app/admin/content/page.tsx:90,150-172 | setContentItems((previousItems) => [...previousItems, newItem]) | Uploaded content is persisted server-side and available after reload/to other users. | Upload is purely client-side state; refresh loses everything. No Prisma model backs content. | Add a Content Prisma model, storage (e.g. S3/blob) + API route, and wire the upload form to it. | High | Fixed 2026-09-01 — added ContentResource Prisma model + /api/admin/content (GET/POST) and /api/admin/content/[id] (DELETE). No object-storage provider was configured, so resources persist as metadata + an optional external URL rather than uploaded binary files.
GAP-004 | Admin | Content Library | 'Preview Assets' button is a no-op. | Dead Action (No-op) | Low | Fixed | src/app/admin/content/page.tsx:379-384 | onClick={() => { console.log(`Preview ${category.title}`); }} | Clicking Preview opens/shows the asset category contents. | Click only logs to console; no UI effect. | Implement a preview modal/drawer once Content backend (GAP-003) exists. | Low | Fixed 2026-09-01 — Preview Assets now toggles a real inline panel listing that category's persisted resources instead of logging to console.
GAP-005 | Admin | Course Management | Courses page lists from a permanently empty mock array; 'Create Course' fakes a save; no Course model exists in the schema. | Mock/Hardcoded Data | Critical | Fixed | src/app/admin/courses/page.tsx:6,22-24; src/data/admin/tables.ts:82; prisma/schema.prisma | import { mockCourses } ...; "In production: POST to /api/editor/courses or equivalent"; mockCourses: CourseRow[] = []; no "model Course" in schema.prisma | Courses list and creation are backed by a real Course model and CRUD API. | List is always empty; creation shows a fake 700ms-delay success toast and saves nothing. | Add a Course Prisma model + migration, build CRUD API routes, connect the page to them. | High | Fixed 2026-09-01 — added Course Prisma model + /api/admin/courses (GET/POST) and /api/admin/courses/[id] (PATCH/DELETE); Courses page now lists, creates, edits and deletes real records. enrolledStudents/lessonsCount are computed live (student grade counts + real editor lesson-file counts per grade) via a single groupBy each, not stored zero fields.
GAP-006 | Admin | Payments | Payments page has no backend; 'Generate Invoice' is a no-op; no Payment/Transaction model exists. | Missing Backend | Critical | Fixed | src/app/admin/payments/page.tsx:32,134-136; prisma/schema.prisma | const handleGenerateInvoice = () => { console.log("Generate Invoice"); }; no "model Payment" in schema.prisma | Payments/invoices are tracked in the DB and the page reflects real transaction data. | Page shows empty local state only; invoice generation just logs to console. | Design a Payment/Invoice data model (or integrate a payments provider), add API routes, wire the UI. | High | Fixed 2026-09-01 — added Payment Prisma model + /api/admin/payments (GET/POST); Generate Invoice now opens a form that creates a real payment/invoice record.
GAP-007 | Admin | Reports | Report cards are static config; Download/Export buttons are no-ops; no Report model exists. | Dead Action (No-op) | Critical | Fixed | src/app/admin/reports/page.tsx:33-40,69-71; src/data/admin/reports.ts | "Backend / actual PDF or CSV download can be connected later." | Reports are generated from real data and downloadable as PDF/CSV. | Buttons only console.log; report list is static, not DB-backed. | Define reportable datasets, add a generation/export API (PDF/CSV), wire buttons to it. | High | Fixed 2026-09-01 — added /api/admin/reports/export (CSV) sourced from real DB data (users, schools, payments, security/role counts); Download and Export All now stream real files instead of logging.
GAP-008 | Admin | School Management | Schools page lists from a permanently empty mock array; 'Onboard School' simulates a save; no School model exists. | Mock/Hardcoded Data | Critical | Fixed | src/app/admin/schools/page.tsx:6,28-30; src/data/admin/tables.ts:32; prisma/schema.prisma | "In production: POST to /api/admin/schools — for now we simulate success"; await new Promise(r => setTimeout(r, 800)); mockSchools: SchoolRow[] = [] | Schools are created/listed via a real School model and API. | List is always empty; onboarding shows a fake delayed success and persists nothing. Schools are only referenced as free-text strings on profiles. | Add a School Prisma model + relations to TeacherProfile/StudentProfile, build CRUD API, wire the page. | High | Fixed 2026-09-01 — added School Prisma model + /api/admin/schools (GET/POST) and /api/admin/schools/[id] (PATCH/DELETE); Schools page now lists, onboards, edits and deletes real records. teachersCount/studentsCount are computed live from real TeacherProfile/StudentProfile matches (two groupBy queries, not stored zero fields).
GAP-009 | Admin | Student Management | 'Add Student' assigns the same hardcoded temporary password to every admin-created student. | Security Weakness | Medium | Fixed | src/app/admin/students/page.tsx:22-39 | password: "Student@Intellia360!" | Each admin-created account gets a unique, randomly generated temporary password (or an invite/set-password-on-first-login flow). | Every new student shares one fixed literal password, a credential-stuffing/predictability risk. | Generate a random temp password per user, or move to an invite-link/first-login-set-password flow. | Low | Fixed 2026-09-01 — Add Student now generates a unique crypto-random temp password per account instead of a shared hardcoded literal (same fix applied to Invite Teacher).
GAP-010 | Admin | Teacher Management | 'Invite Teacher' registers the account with role STUDENT (register API can't set TEACHER); admin must manually upgrade the role afterward, with no guided step. | Incomplete Flow | High | Fixed | src/app/admin/teachers/page.tsx:37,44-50 | "Upgrade their role to TEACHER via admin API (register creates STUDENT; admin must assign the role)" | Inviting a teacher creates (or upgrades) the account directly with role TEACHER in one flow. | New account is created as STUDENT; promoting to TEACHER is a separate untriggered manual step. | Extend the invite flow to call the role-update API automatically after registration, or add an admin-only create-with-role endpoint. | Medium | Fixed 2026-09-01 — register API now returns the new userId; Invite Teacher immediately calls the existing PATCH /api/admin/users/[userId]/role endpoint to upgrade the account to TEACHER in the same flow.
GAP-011 | Admin | Schools/Teachers/Students/Courses Lists | List views for Schools, Teachers, Students, and Courses all render from permanently empty hardcoded arrays instead of live data. | Mock/Hardcoded Data | Critical | Fixed | src/data/admin/tables.ts:32,48,65,82 (mockSchools/mockTeachers/mockStudents/mockCourses) | mockSchools/mockTeachers/mockStudents/mockCourses are all defined as empty arrays and referenced directly by the respective page components. | Each list fetches and displays real records from the database (e.g. GET /api/admin/users for teachers/students). | All four tables are permanently empty regardless of actual DB contents. | Replace mock array imports with real API fetches (existing /api/admin/users for teachers/students; new endpoints for schools/courses per GAP-005/GAP-008). | Medium | Fixed 2026-09-01 — src/data/admin/tables.ts rewritten to fetch live data (new /api/admin/schools, /api/admin/courses; extended /api/admin/users with role-scoped profile fields for teachers/students). ReusableTable extended with a real row-actions menu; Schools and Courses now also support Edit and Delete, not just List/Create.
GAP-012 | Admin | Platform Settings | 'Save Settings' only logs to console and shows a fake success toast; nothing persists. | Dead Action (No-op) | High | Fixed | src/app/admin/settings/page.tsx:116-145 | console.log("Platform Settings:", settings); setSaved(true); | Settings changes are saved server-side and survive page reload. | Settings silently reset to defaults on every reload; the 'Saved' confirmation is misleading. | Add a Settings model/API and persist on save; load persisted values on mount. | Medium | Fixed 2026-09-01 — added AdminSettings (singleton) Prisma model + /api/admin/settings (GET/PUT); Save Settings now persists and the page loads saved values on mount.
GAP-013 | Admin | Admin Dashboard KPIs | Hero/KPI/platform-health data-fetch functions are stubs that always return static zero objects. | Mock/Hardcoded Data | High | Fixed | src/data/admin/dashboard.ts:222-260 | // These functions DO NOT make API/backend requests. | Dashboard KPIs reflect real aggregate platform data. | fetchHeroData/fetchKpiStats/fetchPlatformHealth never call an API; dashboard always shows zeros. | Implement real aggregation endpoints (user counts, activity, health) and call them from these functions. | High | Fixed 2026-09-01 — added /api/admin/stats aggregation endpoint (shared by Dashboard, Analytics, Profile); hero/KPI cards and platform health (server/DB/API) now reflect real counts, with unmeasured integrations (storage, backups, AI gateway) left as 'Checking' rather than fabricated.
GAP-014 | Admin | Admin Profile | Admin Profile page pulls 'Total Users'/'Total Grades' from the Editor module's stats endpoint rather than an admin-owned one. | Incomplete Flow | Low | Fixed | src/app/admin/profile/page.tsx:12 | fetch("/api/editor/stats") | Admin-facing stats are served by an admin-scoped endpoint. | Works today but couples the Admin module to Editor internals. | Add a dedicated /api/admin/stats endpoint (can reuse the same logic) and point the page at it. | Low | Fixed 2026-09-01 — Profile page now calls the new /api/admin/stats endpoint instead of /api/editor/stats, removing the cross-module coupling.
GAP-015 | Teacher | Classes Roster | Classes page is an empty scaffold with no roster UI or data. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/teacher/classes/page.tsx:1-7 | {/* Teacher Classes Roster Scaffold */} | Teacher can view/manage their class roster (backed by the existing ClassGroup Prisma model). | Page renders nothing but a comment; nav link is effectively dead. | Build the roster UI and an /api/teacher/classes endpoint against the existing ClassGroup model. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-016 | Teacher | Assignments | Assignments page is an empty scaffold; no create/list/grade functionality despite Assignment + AssignmentSubmission models existing. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/teacher/assignments/page.tsx:1-7 | {/* Teacher Assignments Scaffold */} | Teacher can create assignments and review/grade student submissions. | Page renders nothing; no API route exists for assignments anywhere in src/app/api. | Build assignment CRUD + submission/grading UI and API routes against existing Assignment/AssignmentSubmission models. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-017 | Teacher | Analytics | Analytics page is an empty scaffold despite ClassGroup/QuizAttempt data existing to support it. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/teacher/analytics/page.tsx:1-7 | {/* Teacher Analytics Scaffold */} | Teacher sees class/student performance analytics. | Page renders nothing; no backing API route exists. | Build an aggregation API over QuizAttempt/CompletedLesson data scoped to the teacher's classes, and the analytics UI. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-018 | Teacher | AI Lesson Planner | AI Planner page is an empty scaffold; no form, no AI/LLM integration, and no backend route exists. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/teacher/ai-planner/page.tsx:1-7 | {/* Teacher AI Lesson Planner Scaffold */} | Teacher can generate lesson plans via an AI/LLM-backed tool. | Feature does not exist beyond the nav entry; no LLM integration anywhere in the codebase for this. | Design the planner UI, add an LLM-backed API route, and define what curriculum context feeds the prompt. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-019 | Teacher | Teacher Profile | Profile page is an empty scaffold despite a TeacherProfile model (schoolName, avatar) existing. | Empty Scaffold (Missing Feature) | High | Not Implemented | src/app/teacher/profile/page.tsx:1-7 | {/* Teacher Profile Scaffold */} | Teacher can view/edit their profile (name, school, avatar, password). | Page renders nothing; only /api/teacher/me exists (dashboard read, not profile edit). | Build profile view/edit UI and a PATCH endpoint against TeacherProfile, mirroring the student profile flow. | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-020 | Teacher | Dashboard KPIs | 'Avg Completion' stat card always shows 0% — the backend hardcodes it rather than computing it. | Mock/Hardcoded Data | Medium | Partially Implemented | src/app/api/teacher/me/route.ts:46 | averageCompletion: 0, // would be computed from quiz attempts in a full implementation | Average completion is computed from real QuizAttempt/CompletedLesson data for the teacher's classes. | Value is always 0 regardless of actual student activity. | Compute averageCompletion from QuizAttempt/CompletedLesson records scoped to the teacher's ClassGroups. | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-021 | Teacher | Dashboard Empty State | 'No classes yet' empty-state card renders unconditionally, ignoring the actual totalClasses count returned by the API. | UI State Gap | Low | Partially Implemented | src/app/teacher/dashboard/page.tsx:199-209 | stats.totalClasses is fetched but never used to conditionally hide/show the empty-state block | Empty state only shows when the teacher genuinely has zero classes. | Empty state always displays, even if classes exist. | Gate the empty-state block on stats.totalClasses === 0. | Low | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-022 | Student | Rewards | Rewards page is an empty scaffold with no UI, data, or backend calls. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/student/rewards/page.tsx:1-7 | {/* Student Rewards & Missions Scaffold */} | Student can view earned badges/rewards and mission progress in one place. | Page renders nothing; nav link is dead. | Build the rewards/missions UI against the existing /api/student/badges and /api/student/missions endpoints (both already functional). | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-023 | Student | Worksheets | Worksheets page is an empty scaffold; no Worksheet model exists in the schema at all. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/student/worksheets/page.tsx:1-7 | {/* Student Worksheets Scaffold */} | Student can browse/download worksheets tied to their grade/curriculum. | Feature does not exist beyond the nav entry; no schema support. | Add a Worksheet model (or reuse EduNote-style file storage), build listing/download API and UI. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-024 | Student | Courses | Courses page is an empty scaffold with no listing or data. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/student/courses/page.tsx:1-7 | {/* Student Courses Scaffold */} | Student can browse enrolled/available courses. | Page renders nothing. | Define course data source (depends on GAP-005 Course model or curriculum/grade structure) and build the listing UI. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-025 | Student | Quiz Taking | Quiz [id] page is an empty scaffold; the dashboard's 'Practice' CTA links to it and hits a dead route. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/student/quiz/[id]/page.tsx:1-7 | {/* Student Quiz Scaffold */} — dashboard practiceUrl = "/student/quiz/practice-1" | Student can take a practice/assigned quiz by ID and submit answers via /api/student/quiz-attempts. | Route renders nothing; the working quiz-attempts API has no UI to call it outside Daily Quiz. | Build the quiz-taking UI for this route, reusing the Daily Quiz UI pattern and the existing quiz-attempts API. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-026 | Student | Lesson Player | Lesson [id] page is an empty scaffold; no lesson content renders despite dashboard cards linking to lesson URLs. | Empty Scaffold (Missing Feature) | Critical | Not Implemented | src/app/student/lesson/[id]/page.tsx:1-7 | {/* Student Lesson Player Scaffold */} | Student can view/play lesson content and mark it complete via /api/student/activities/complete. | Route renders nothing; lesson links from the dashboard lead to a blank page. | Build the lesson player UI (video/content viewer) wired to editor-authored lesson content and the completion API. | High | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-027 | Student | Badge Sync | Unlocked badges are loaded only from localStorage; the working GET /api/student/badges endpoint is never called. | Broken Link (Integration Gap) | High | Partially Implemented | src/app/student/profile/page.tsx:156-166; src/context/StudentContext.tsx:182-198 | if (Array.isArray(parsed.unlockedBadges)) setUnlockedBadges(parsed.unlockedBadges); — no fetch of /api/student/badges anywhere | Badges are fetched from the server on load and stay in sync across devices/browsers. | Badges are purely local; clearing browser storage or switching devices loses/desyncs badge state. | Fetch /api/student/badges on StudentContext init and use it as the source of truth instead of (or merged with) localStorage. | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-028 | Student | Missions | A fully working Missions API (GET/PATCH with DB persistence + notifications) exists but no page or component ever calls it. | Dead Feature (Unused Backend) | Medium | Implemented Not Wired | src/app/api/student/missions/route.ts | grep for '/api/student/missions' across src/ returns only the route file itself. | Students see and progress through missions in the UI. | Backend logic is complete and unused; no UI surface exists. | Surface missions in the Rewards page (GAP-022) or Dashboard, calling the existing API. | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-029 | Student | Badge Unlocking | Client-side unlockBadge() only updates React state; it never POSTs to persist the unlock server-side. | Broken Link (Integration Gap) | Medium | Partially Implemented | src/context/StudentContext.tsx:316-323 | const unlockBadge = (badgeId) => { setUnlockedBadges((prev) => {...}) }; — no API call | Unlocking a badge persists it via the badges API so it survives reload/syncs across devices. | Unlock is visible only in the current session's local state. | Have unlockBadge() call POST/PATCH /api/student/badges in addition to updating local state. | Low | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-030 | Student | Dashboard Analytics | 'Learning Progress' bar chart and 'Lesson Distribution' donut are computed from arbitrary multipliers of completed-lesson count, not real historical data. | Data Integrity/Fabricated Metrics | Medium | Partially Implemented | src/app/student/dashboard/page.tsx:293-320 | const base = Math.max(completedLessons.length, 1); const chartBars = [Math.round(base * 0.5), ...] | Charts reflect real time-series/subject-distribution data from the DB. | Chart shapes are synthetically derived and presented as if they were real analytics. | Track lesson completions with real timestamps/subject tags and aggregate them server-side for the chart. | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-031 | Student | Leaderboard | Weekly and Monthly leaderboard tabs are permanently disabled ('Coming Soon'). | Empty Scaffold (Missing Feature) | Low | Not Implemented | src/app/student/leaderboard/page.tsx:161-176 | Weekly (Coming Soon) / Monthly (Coming Soon) | Weekly/Monthly leaderboard views are selectable and populated. | Only the All-Time tab works; the other two are inert. | Add date-windowed leaderboard queries and enable the tabs. | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-032 | Editor | Route Access Control | Editor pages have no page-level session/role guard (API layer is protected, page shell is not). | RBAC Gap | Medium | Partially Implemented | src/app/editor/layout.tsx | EditorLayout is a client component with only handleLogout — no session/role check or redirect. | Non-editor/admin users are redirected before the editor page shell renders. | Page shell loads for anyone; underlying data calls are blocked via requireEditorSession() but the UI briefly renders empty/errored states instead of redirecting. | Add a server-side session/role check in the editor layout (or middleware.ts) mirroring requireEditorSession(). | Medium | Open — outside the 2026-09-01 remediation session's scope (Admin module only).
GAP-033 | Editor | Lesson Creation Link | '+ New Lesson' link points to /editor/lessons/new, a route that does not exist. | Broken Link | Low | Broken | src/app/editor/courses/page.tsx:64 | <Link href="/editor/lessons/new" className="ed-btn-primary">+ New Lesson</Link> | Link navigates to a working lesson-creation flow. | Clicking it 404s — only /editor/lessons and /editor/lessons/[gradeId]/[lessonId] exist. | Point the link at the correct existing route, or build the missing /editor/lessons/new creation flow. | Low | Open — outside the 2026-09-01 remediation session's scope (Admin module only).

## Module Status
Module | Pages Total | Fully Working | Partially Working | Broken/Empty | Gap Count | Completion % | Notes
Authentication | 6 | 6 | 0 | 0 | 0 | 100% | Login/register/password-reset/verify-email flows, Google OAuth, JWT/session, Zod validation, and Resend-based email delivery are all fully implemented and verified working. No gaps found.
Admin | 11 | 11 | 0 | 0 | 0 | 100% | Fixed 2026-09-01 (all 14 gaps resolved): server-side RBAC guard added; School/Course/Payment/ContentResource/AdminSettings Prisma models added; Schools, Courses, Content, Payments, Settings, Reports now have real CRUD/export; Dashboard, Analytics and Profile share a new /api/admin/stats endpoint; Students/Teachers use unique per-account temp passwords, and Invite Teacher now assigns the correct role automatically.
Editor | 8 | 7 | 1 | 0 | 2 | 88% | Grades, Lessons, Curriculum, Users, Courses all have real CRUD wired to Prisma-backed or filesystem-backed APIs. Only a page-level RBAC gap and one broken link found.
Teacher | 6 | 0 | 1 | 5 | 7 | 14% | Only Dashboard is functional (and one of its stats is hardcoded). Classes, Assignments, Analytics, AI Planner, and Profile are all empty scaffolds despite supporting Prisma models (ClassGroup, Assignment, AssignmentSubmission, TeacherProfile) existing for most of them.
Student | 13 | 5 | 3 | 5 | 10 | 62% | Daily Quiz, Notifications, Profile, and EduNotes are fully working; Leaderboard and Dashboard are partially working (fabricated chart data / disabled tabs). Rewards, Worksheets, Courses, Quiz-by-id, and Lesson Player are empty scaffolds; Missions API is built but has no UI.

## Priority Roadmap
Priority | Status | Theme | Related Gap IDs | Rationale | Estimated Effort
P1 - Critical | Open | Stand up empty scaffold pages that block core flows | GAP-022 Rewards, GAP-024 Courses (Student), GAP-025 Quiz Taking, GAP-026 Lesson Player, GAP-015 Teacher Classes, GAP-016 Teacher Assignments, GAP-017 Teacher Analytics, GAP-018 AI Planner | These are dead nav entries on the two highest-traffic roles (Student, Teacher); Quiz/Lesson pages are linked directly from the dashboard, so students currently hit blank pages mid-flow. | Large (6-10 weeks)
P1 - Critical | Completed 2026-09-01 | Replace Admin mock data with real models + APIs | GAP-005 Courses, GAP-006 Payments, GAP-007 Reports, GAP-008 Schools, GAP-011 List views | Entire Admin operational area (schools, courses, payments, reporting) was non-functional — no schema, no persistence, list views permanently empty, blocking any real admin usage of the platform. | Completed — School/Course/Payment Prisma models + /api/admin/{schools,courses,payments,reports/export} added; all four list views now DB-backed.
P2 - High | Completed 2026-09-01 | Wire up Admin dashboard/content/settings persistence + Teacher invite role | GAP-002 Analytics, GAP-003 Content Upload, GAP-012 Settings, GAP-013 Dashboard KPIs, GAP-010 Teacher Invite role | These were functional but disconnected — the UI existed, only the backend wiring/persistence was missing. | Completed — AdminSettings + ContentResource models added, /api/admin/{content,settings,stats} added, Invite Teacher now auto-assigns the TEACHER role via the existing role-change API.
P2 - High | Open | Build Teacher Profile page | GAP-019 Teacher Profile | TeacherProfile model (schoolName, avatar, subject) already exists but has no view/edit UI — the only Admin-adjacent P2 item not in this session's Admin-only scope. | Medium (1-2 weeks)
P2 - High | Open | Fix Student badge/reward data integrity | GAP-023 Worksheets, GAP-027 Badge Sync | Badge state currently lives only in localStorage, risking data loss across devices; Worksheets has zero backend and needs schema design. | Medium (2-3 weeks)
P3 - Medium | Completed 2026-09-01 | Admin RBAC guard + unique per-account temp passwords | GAP-001 Admin RBAC, GAP-009 Shared temp password | Page-level RBAC gap and a predictable shared password were the two Admin-scoped correctness/security issues in this bucket. | Completed — src/app/admin/layout.tsx server guard added; Add Student / Invite Teacher now generate unique random temp passwords.
P3 - Medium | Open | Close remaining integration and data-integrity gaps | GAP-032 Editor RBAC, GAP-020 Avg Completion, GAP-028 Missions UI, GAP-029 Badge persistence, GAP-030 Fabricated dashboard charts | Real but lower-visibility correctness issues outside Admin: an Editor page-level RBAC gap, a hardcoded Teacher stat, an unused Missions API, and synthetically-derived Student dashboard charts. | Medium (2-3 weeks)
P4 - Low | Completed 2026-09-01 | Admin content preview + profile stats source | GAP-004 Preview Assets, GAP-014 Admin Profile coupling | Low-impact Admin polish items, fixed alongside the rest of the Admin remediation. | Completed — Preview Assets now shows real category items; Profile now reads /api/admin/stats instead of the Editor module's endpoint.
P4 - Low | Open | Polish remaining dead links and disabled tabs | GAP-021 Dashboard empty state, GAP-031 Leaderboard tabs, GAP-033 New Lesson link | Low-impact issues that don't block core flows; suitable for a cleanup sprint once higher-priority gaps are resolved. | Small (1 week)