## Summary
Intellia360 — Functionality Checklist
Features built or fixed on branch feature/authentication. Last verified 15 Sep 2026 on a local dev server (Windows).
Area (sheet) | What it covers | Checks | Pass | Verified in code | Not tested | Known limitation
Admin-only user and role management; Users removed from the Editor
Lesson module links, validation and saving (local and read-only server)
Architecture / Videos / EduNotes inside /student/lesson/[id]
EduNotes PDFs and lesson videos
Curriculum and Grades editors, including read-only server support
Total
Result legend
Pass | Tested in this session (browser, API call or script) and worked.
Verified in code | Implemented and type-checked/linted, but not exercised end-to-end.
Not tested | No verification yet.
Known limitation | Works, with a documented limit or external constraint.
See also
Per-grade lesson data resolution results
Open issues and suggested next steps

## User Management
ID | Functionality | Who uses it | How to use / steps | Expected result | Test method | Result | Evidence / notes | Key files
UM-01 | Users page removed from the Editor console | Editor | Log in as an Editor and open the sidebar and dashboard. | No Users link, no user count, no 'Users by Role' panel; Editor sees content tools only. | Code review + type check | Verified in code | Page, nav link, dashboard widgets and user stats removed. Not clicked through in a browser. | src/app/editor/layout.tsx; src/app/editor/dashboard/page.tsx; src/app/api/editor/stats/route.ts
UM-02 | Editor user APIs removed | Editor | Call GET/POST /api/editor/users or PATCH/DELETE /api/editor/users/[id]. | Routes no longer exist (404). Editors can no longer create ADMIN accounts. | Code review | Verified in code | Route files deleted. | src/app/api/editor/users/** (deleted)
UM-03 | Users & Roles page lists every account | Admin | Admin → People → Users → All Users & Roles. Search by name/email, filter by role, tick 'Show deactivated', page through results. | Table shows name, email, role, status (Active / Unverified / Deactivated) and joined date; filters and paging update the list. | Type check + lint | Verified in code | Not browser-tested. | src/app/admin/users/page.tsx; src/app/api/admin/users/route.ts
UM-04 | Summary cards filter the table | Admin | Click the Total users / Role requests / Admins / Editors cards. | Table filters to that group; the active card is highlighted. | Type check + lint | Verified in code | Not browser-tested. | src/app/admin/users/page.tsx
UM-05 | Change a user's role | Admin | Click 'Change role', pick a role, click Save role. | Role updated; extra confirmation when granting ADMIN; an admin cannot remove their own ADMIN role; takes effect at the user's next sign-in. | Type check + lint | Verified in code | Uses the existing PATCH /api/admin/users/[id]/role (audited). | src/app/admin/users/page.tsx; src/app/api/admin/users/[userId]/role/route.ts
UM-06 | Approve a pending role request | Admin | Open the 'Role requests' tab, click 'Approve <ROLE>'. | User gets the requested role and leaves the pending list. | Type check + lint | Verified in code | Not browser-tested. | src/app/admin/users/page.tsx
UM-07 | Deactivate and restore an account | Admin | Click Deactivate (confirm). Tick 'Show deactivated', click Restore. | Account marked Deactivated with history kept; Restore brings it back. An admin cannot deactivate themselves. | Type check + lint | Verified in code | Uses the existing soft-delete API. | src/app/api/admin/users/[userId]/route.ts
UM-08 | Permanently delete a deactivated account | Admin | Tick 'Show deactivated' → 'Delete forever' → confirm. | Only allowed for already-deactivated accounts; history erased; audit entry records what was destroyed. | Type check + lint | Verified in code | Not browser-tested. | src/app/api/admin/users/[userId]/route.ts
UM-09 | Create a user with a role | Admin | Click '+ New User', enter name, email, password and role → Create user. | Account created with the role and its profile; same password rules as sign-up; duplicate email rejected; audit entry written. | Type check + lint | Verified in code | POST /api/admin/users. Not browser-tested. | src/app/api/admin/users/route.ts; src/data/admin/tables.ts

## Lesson Editor
ID | Functionality | Who uses it | How to use / steps | Expected result | Test method | Result | Evidence / notes | Key files
LE-01 | Module URL fields accept site paths and full links | Editor | Editor → Lessons → Edit lesson → Module URLs. Enter e.g. https://placetens.vercel.app/ or /student/quiz/practice-1. | Save is no longer blocked by the browser's URL check; the value is saved exactly. | API call (Editor save) | Pass | Saved Architecture https://number-counting-gamma.vercel.app/ and Video https://www.youtube.com/watch?v=6hyYVLv8hzY → 200 'Lesson saved.' | src/app/editor/lessons/[gradeId]/[lessonId]/page.tsx
LE-02 | Link required only when the module is Enabled | Editor | Untick Enabled and leave the link empty → Save. Tick Enabled with an empty link → Save. | Disabled + empty saves fine; Enabled + empty shows 'Add a link, or untick Enabled.' | Validation script | Pass | Both cases checked. | src/lib/content/lesson-modules.ts
LE-03 | Invalid link formats rejected | Editor | Enter 'student/lesson', '//evil.com' or 'javascript:alert(1)'. | Field error: use a site path or a full https:// link. | Validation script | Pass | All three rejected; /student/lesson/video and https links accepted. | src/lib/content/lesson-modules.ts
LE-04 | Architecture / Video links limited to embeddable sites | Editor | Enter an Architecture link on another site, e.g. https://example.com/lesson → Save. | 422 with a message; allowed sites are *.vercel.app, YouTube (incl. youtu.be) and Google Drive. | API call + validation script | Pass | example.com → 422 'Students can't open this site inside the lesson…'; lesson file unchanged. vimeo.com video rejected; youtu.be and Drive accepted. | src/lib/content/lesson-modules.ts; next.config.ts (frame-src)
LE-05 | Save writes the lesson JSON (local / writable server) | Editor | Save a lesson on a local dev server. | Lesson JSON file contains the saved values; response storedIn = file. | API call + file check | Pass | grade1/lessons/counting-up-to-100.json contained both saved URLs; practiceModule unchanged. | src/lib/content/lesson-store.ts; src/lib/content/curriculum-store.ts
LE-06 | Save works on a read-only server (Vercel) | Editor | Save a lesson on the deployed site. | Saved to the database instead of failing with 'Save failed (500)'; the message says it was saved to the database. | Read-only simulation script | Pass | Store forced read-only: save → storedIn database, no file written. Not yet tested on a real Vercel deploy. | src/lib/content/curriculum-store.ts; src/app/api/editor/lessons/[gradeId]/[lessonId]/route.ts
LE-07 | Save errors shown instead of a stuck 'Saving…' | Editor | Trigger a failing save (e.g. a server error). | Message explains the failure (e.g. read-only filesystem, database unreachable); the button re-enables. | Code review | Verified in code | The earlier 'Save failed (500)' screenshot showed the error surfacing instead of hanging. | src/app/editor/lessons/[gradeId]/[lessonId]/page.tsx
LE-08 | Form and Raw JSON tabs stay in sync | Editor | Edit in Form, switch to Raw JSON (and back), save from either tab. | Unsaved edits carry across tabs; saving one tab never writes stale values from the other. | Code review | Verified in code | Not browser-tested. | src/app/editor/lessons/[gradeId]/[lessonId]/page.tsx
LE-09 | Lesson list includes database-only lessons | Editor | On a read-only server, create a lesson and open the grade's lesson list. | The new lesson appears in the list. | Read-only simulation script | Pass | listLessons(grade99) → ['test-topic']. | src/lib/content/lesson-store.ts
LE-10 | Delete a lesson | Editor | Lessons list → Delete. | Locally the file is removed; on a read-only server a tombstone hides it. Content stays recoverable from the mirror. | Read-only simulation script | Pass | Read-only delete → readLesson returns null, list empty. | src/lib/content/lesson-store.ts
LE-11 | Create a lesson | Editor | Lessons → create form (id, title, chapter, URLs). | Lesson created; a module is only enabled when it was given a link. | Code review | Verified in code | POST route not called in tests. | src/app/api/editor/lessons/[gradeId]/route.ts
LE-12 | Existing lesson files pass the new validation | Editor | Open and save any existing lesson. | No validation errors on existing data. | Validation script | Pass | All 8 lesson files (Grade 1 ×7, Grade 2 ×1) OK. | src/data/grades/*/lessons/*.json

## Student Lesson Page
ID | Functionality | Who uses it | How to use / steps | Expected result | Test method | Result | Evidence / notes | Key files
SL-01 | Architecture loads the Editor-saved URL | Student | Open /student/lesson/counting-numbers-up-to-100 (Lesson button). | Interactive lesson framed inside the Lesson Player card, using the URL from lesson data. | Browser (headless Chrome) | Pass | iframe src = https://number-counting-gamma.vercel.app/ (hard-coded URL map removed). | src/app/student/lesson/[id]/page.tsx; src/lib/student/lesson-resources.ts
SL-02 | Videos button plays the Editor-saved video in the lesson page | Student | Click 'Videos' on the lesson page. | URL becomes ?module=video; the YouTube video plays in the existing video player. | Browser (headless Chrome) | Pass | iframe youtube-nocookie.com/embed/6hyYVLv8hzY. | src/app/student/lesson/[id]/page.tsx
SL-03 | EduNotes button opens the book in the lesson page | Student | Click 'EduNotes', then 'Open Book →'. | EduNotesBookViewer opens inside the lesson page and PDF pages render. | Browser (headless Chrome) | Pass | 13-page book; PDF canvases rendered. | src/app/student/lesson/[id]/page.tsx; src/components/student/EduNotesBookViewer.tsx (unchanged)
SL-04 | One Header and Sidebar only | Student | Switch between Lesson, Videos and EduNotes. | No student route is framed inside another; exactly one Header and Sidebar. | Browser (headless Chrome) | Pass | student-shell count = 1 on every module. | src/components/student/LessonResourceNav.tsx
SL-05 | Unavailable modules show the existing states | Student | Open a lesson whose modules are disabled, e.g. numbers-and-counting-test-series. | 'Lesson Architecture Coming Soon', 'Videos coming soon', 'EduNotes not available' — no crash. | Browser (headless Chrome) | Pass | All three states shown. | src/app/student/lesson/[id]/page.tsx
SL-06 | Lesson uses the student's own grade (no wrong-grade flash) | Student | Open a lesson link without ?grade=. | Lesson data is requested once, with the grade from the student profile. | Browser (headless Chrome) | Pass | Cached grade3 + profile grade1 → single request grade=grade1 (lesson and video pages). | src/context/StudentContext.tsx (gradeReady); src/app/student/lesson/[id]/page.tsx
SL-07 | Module buttons carry the grade | Student | Inspect the Lesson / Videos / EduNotes button links. | Links are /student/lesson/<id>?module=…&grade=<grade>. | Browser (headless Chrome) | Pass | All three hrefs include grade=grade1. | src/components/student/LessonResourceNav.tsx
SL-08 | Grade 2 lesson loads Grade 2 data | Student | Open /student/lesson/counting-numbers-up-to-200?grade=grade2. | The Grade 2 interactive lesson loads. | Browser (headless Chrome) | Pass | iframe src = https://grade2-numbers-to-200.vercel.app/. | src/lib/student/lesson-resources.ts
SL-09 | Lesson files with a different ID still match their topic | Student | Open reading-and-writing-numbers or ordinal-numbers-first-second-third. | Lesson file matched by title; EduNotes found. | API call | Pass | Both resolved with EduNotes available. | src/lib/student/lesson-resources.ts
SL-10 | Old /student/lesson/architecture link forwards | Student | Open /student/lesson/architecture?lessonId=counting-numbers-up-to-100. | Redirects to /student/lesson/counting-numbers-up-to-100 and loads the architecture. | Browser (headless Chrome) | Pass | Hard-coded URL removed from that route. | src/app/student/lesson/architecture/page.tsx
SL-11 | Unknown lesson, bad grade and no session handled | Student | Request an unknown lesson id, an invalid grade, or call the API signed out. | Unknown → unavailable (found:false); invalid grade → 400; signed out → 401. | API call | Pass | no-such-lesson found:false; ../../etc → 400; no cookie → 401. | src/app/api/student/lesson-resources/route.ts
SL-12 | Practice stays stored but is not shown in the lesson page | Student | Save a lesson in the Editor; open the lesson page. | Practice URL retained in lesson data; the lesson page shows only Lesson / Videos / EduNotes. | API call + code review | Pass | practiceModule unchanged after the Editor save. | src/lib/student/lesson-resources.ts
SL-13 | Links on non-embeddable sites show 'unavailable' instead of a blank frame | Student | Lesson data containing a link on a site the CSP does not allow. | Falls back to the next source or the unavailable state. | Code review | Verified in code | No such links exist in current data. | src/lib/student/lesson-resources.ts

## EduNotes & Videos
ID | Functionality | Who uses it | How to use / steps | Expected result | Test method | Result | Evidence / notes | Key files
EV-01 | EduNotes from the existing Drive registry | Student | Open EduNotes for a Grade 1 lesson with a registered PDF. | Metadata 200; PDF served as application/pdf. | API call | Pass | counting-numbers-up-to-100: 18,764,667 bytes, starts with %PDF-. | src/lib/student/edunotes.ts; src/app/api/student/edunotes/**
EV-02 | EduNotes link added in the Editor (Google Drive) | Editor | Paste the Drive 'Copy link' URL into the lesson's EduNotes field, tick Enabled, Save. | Accepted formats: drive.google.com/file/d/<ID>/view, open?id=<ID>, uc?export=download&id=<ID>. The book opens with that PDF. | Code review | Verified in code | Not yet tested end-to-end with a new Drive link. | src/lib/student/lesson-resources.ts
EV-03 | Drive file requirements | Editor | Before pasting a link, check the file. | Must be a PDF, shared 'Anyone with the link – Viewer', one file per lesson, under ~100 MB. | Guidance | Known limitation | Restricted files, Google Docs links and folder links will not open.
EV-04 | EduNotes PDF is streamed | Student | Open a large EduNotes book. | Bytes stream to the browser instead of being buffered; stays under serverless response limits. | API call | Pass | First chunk 7.7 s, complete 13.0 s, full 18.7 MB received. | src/app/api/student/edunotes/content/route.ts
EV-05 | EduNotes fetch retries once on connection failure | Student | The Drive connection drops before the response starts. | One automatic retry before returning an error. | Code review | Verified in code | Failure not reproduced on demand. | src/app/api/student/edunotes/content/route.ts
EV-06 | Standalone EduNotes page still works | Student | Dashboard → EduNotes card (/student/lesson/edunotes?lessonId=…). | Book opens and pages render. | Browser (headless Chrome) | Pass | 2 PDF canvases rendered on the retry run. | src/app/student/lesson/edunotes/page.tsx
EV-07 | Standalone Video page uses the same lesson data | Student | Dashboard → Video card (/student/lesson/video?lessonId=…). | Plays the Editor-saved video; one request with the profile grade. | API call + browser | Pass | /api/student/videos returned 6hyYVLv8hzY; single request grade=grade1. | src/app/api/student/videos/route.ts; src/app/student/lesson/video/page.tsx
EV-08 | YouTube link formats | Editor | Use a watch, youtu.be, shorts or embed link in the Video field. | Played through youtube-nocookie.com in the existing player. | Browser + validation script | Pass | watch link played in the browser; youtu.be accepted by validation. | src/lib/student/lesson-videos.ts
EV-09 | Non-YouTube video on an allowed site | Editor | Video field with e.g. a Google Drive preview link. | Framed in the video area. | Code review | Verified in code | Not browser-tested. | src/app/student/lesson/[id]/page.tsx
EV-10 | Google Drive download speed | Student | Open a large EduNotes PDF. | The book opens. | Observation | Known limitation | ~8 s before the first bytes for 18.7 MB; one ECONNRESET seen earlier (before the retry was added). | src/app/api/student/edunotes/content/route.ts

## Curriculum & Grades
ID | Functionality | Who uses it | How to use / steps | Expected result | Test method | Result | Evidence / notes | Key files
CG-01 | Read a grade's curriculum | Editor | Editor → Curriculum → pick a grade. | curriculum.json loads; an unknown grade returns 404. | API call | Pass | grade1 → 200 (7 chapters); grade42 → 404. | src/app/api/editor/curriculum/[gradeId]/route.ts
CG-02 | Grades list with lesson counts | Editor | Editor → Grades. | All grades listed with lesson counts and a curriculum flag. | API call | Pass | 12 grades; grade1: 7 lessons, grade2: 1. | src/app/api/editor/grades/route.ts
CG-03 | Save / update curriculum on a read-only server | Editor | Edit curriculum JSON on the deployed site → Save. | Saved to the database; reads return the saved version. | Read-only simulation script | Pass | Updated gradeLabel read back as 'Grade 99 Test'. | src/lib/content/curriculum-store.ts
CG-04 | Create a grade on a read-only server | Editor | Editor → Grades → create grade. | Grade created in the database and listed. | Read-only simulation script | Pass | grade99 created (storedIn database), no files written. | src/app/api/editor/grades/route.ts
CG-05 | Delete a grade on a read-only server | Editor | Editor → Grades → delete grade. | Grade hidden by tombstones; student lesson data for it disappears; content stays recoverable. | Read-only simulation script | Pass | grade99 exists → false; student resolver found:false. | src/app/api/editor/grades/[gradeId]/route.ts
CG-06 | Built-in grades still readable | Editor / Student | Open any shipped grade on a read-only server. | Shipped files are used when no database copy exists. | Read-only simulation script | Pass | grade1 exists (shipped file). | src/lib/content/curriculum-store.ts
CG-07 | Save / create / delete on a local writable server | Editor | Use the Curriculum and Grades editors locally. | Files written/removed and mirrored to the database, as before. | Code review | Verified in code | Writes not executed locally, to avoid changing real data. | src/lib/content/curriculum-store.ts
CG-08 | Curriculum JSON shipped with deployed routes | Ops | Deploy to Vercel. | Routes that read src/data/grades at runtime include the JSON files. | Code review | Verified in code | outputFileTracingIncludes added. Not deployed yet. | next.config.ts

## Grades 1-12 Data
Grade | Curriculum topics | Resolved OK (HTTP 200) | With Architecture | With Video | With EduNotes | Nothing configured | Notes
Grade 1 | 31 | 31 | 16 | 1 | 6 | 13 | Video = the lesson saved in the Editor test. EduNotes from the Drive registry (6 lessons).
Grade 2 | 40 | 40 | 40 | 0 | 0 | 0 | Grade 2 lesson verified in the browser.
Grade 3 | 55 | 55 | 25 | 0 | 0 | 30
Grade 4 | 34 | 34 | 31 | 0 | 0 | 3
Grade 5 | 56 | 56 | 56 | 0 | 0 | 0
Grade 6 | 0 | 0 | 0 | 0 | 0 | 0 | Curriculum has no chapters yet.
Grade 7 | 2 | 2 | 2 | 0 | 0 | 0
Grade 8 | 0 | 0 | 0 | 0 | 0 | 0 | Curriculum has no chapters yet.
Grade 9 | 0 | 0 | 0 | 0 | 0 | 0 | Curriculum has no chapters yet.
Grade 10 | 1 | 1 | 1 | 0 | 0 | 0
Grade 11 | 0 | 0 | 0 | 0 | 0 | 0 | Curriculum has no chapters yet.
Grade 12 | 0 | 0 | 0 | 0 | 0 | 0 | Curriculum has no chapters yet.
Total
Every curriculum topic was requested through /api/student/lesson-resources on 15 Sep 2026 (local data); no request failed.

## Known Issues
ID | Issue | Impact | Suggested next step | Status
KI-01 | Changes not yet tested on the Vercel deployment | Read-only (database) storage was only simulated locally. | Deploy, then save a lesson, curriculum and grade on the live site and open the lesson as a student. | Open
KI-02 | Student sidebar/dashboard use the curriculum bundled at build time | Curriculum edits saved on Vercel appear in the sidebar/dashboard only after restoring to files and redeploying (the lesson page itself is live). | Load the curriculum for StudentContext from an API instead of a build-time import. | Open
KI-03 | Only *.vercel.app, YouTube and Google Drive can be framed | Architecture/Video links on other sites are rejected by the Editor. | If another site is needed, add it to frame-src in next.config.ts and EMBEDDABLE_HOSTS in lesson-modules.ts. | Open
KI-04 | Google Drive EduNotes downloads are slow | ~8 s before the first bytes for an 18.7 MB PDF; connections occasionally reset. | Host the PDFs on faster storage or cache them server-side. | Open
KI-05 | Grade 1 counting-up-to-100.json holds the test-saved URLs | Architecture and Video URLs from the screenshot were saved during testing; file indentation changed to 2 spaces. | Keep if intended, or revert the file. | Open
KI-06 | Two lint errors predate these changes | set-state-in-effect in student/lesson/edunotes/page.tsx and in StudentContext's localStorage effect. | Refactor those effects when convenient. | Open
KI-07 | Admin Users & Roles page not browser-tested | Type-checked and linted only. | Click through list, filters, role change, approve, deactivate/restore, delete and create. | Open
KI-08 | 'Add Student' / 'Invite Teacher' use the public sign-up endpoint | With email verification off, sign-up signs in as the new account — likely logs the admin out. | Switch those pages to POST /api/admin/users. | Open
KI-09 | Grades 3–12 have no lesson files | Editor links (including EduNotes) can only be added after creating the lesson in the Editor. | Create lessons with the same ID or title as the curriculum topic. | Open
KI-10 | Grades 6, 8, 9, 11 and 12 curricula are empty | No topics to show students. | Add chapters/topics in the Curriculum editor. | Open